## Forward Traceability
Requirements | Tests | Executions | Defects
AA-56 - [Products section]The products images are not displayed correctly - 1 defect | AA-50 - Verify that images of products are displayed correctly. | Test Execution 1 - FAIL | AA-56 - Done - [Products section]The products images are not displayed correctly
AA-55 - "Add to cart" section | AA-24 - Check whether the user is able to add the item to the cart. | Test Execution 1 - PASS | None
AA-49 - Create test conditions for "Products" section | None | None | None
AA-48 - As a client, I want to be correctly informed about the products in order to decide what to buy. - 1 defect | AA-50 - Verify that images of products are displayed correctly. | Test Execution 1 - FAIL | AA-56 - Done - [Products section]The products images are not displayed correctly
AA-48 - As a client, I want to be correctly informed about the products in order to decide what to buy. | AA-51 - Verify that the prices are displayed correctly. | Test Execution 1 - PASS | None
AA-48 - As a client, I want to be correctly informed about the products in order to decide what to buy. | AA-53 - Verify that production stock information are displayed. | Test Execution 1 - PASS | None
AA-48 - As a client, I want to be correctly informed about the products in order to decide what to buy. | AA-52 - Verify the search bar functionality when using a valid value. | Test Execution 1 - PASS | None
AA-48 - As a client, I want to be correctly informed about the products in order to decide what to buy. | AG-50 - Verify that each product within the "Products" module of the application is associated with the correct and corresponding product image. | None | None
AA-47 - "Products" section | None | None | None
AA-46 - [Checkout flow section]The mandatory fields from "Billing Andress" section are not marked with"*" symbol. - 1 defect | AA-42 - Verify that Name, Street Address, City, State, Country, Postal code is the mandatory field in the Checkout Address page (Billing Address). | Test Execution 1 - FAIL | AA-46 - In Progress - [Checkout flow section]The mandatory fields from "Billing Andress" section are not marked with"*" symbol.
AA-45 - [Checkout flow section]The order has been submitted after the user completed all the fields from checkout page with invalid values. - 1 defect | AA-43 - Verify that error message is displayed when the user enters invalid values in all the fields in the checkout page. | Test Execution 1 - FAIL | AA-45 - In Progress - [Checkout flow section]The order has been submitted after the user completed all the fields from checkout page with invalid values.
AA-37 - [Add to cart section] The input field"Quantity"accept negative value - 1 defect | AA-31 - Verify that the user is able to proceed with a negative number like (-1,-2,-3….) | Test Execution 1 - FAIL | AA-37 - Done - [Add to cart section] The input field"Quantity"accept negative value
AA-36 - Create test conditions for "check out flow" section | None | None | None
AA-35 - As a registered client I want to be able to pay for my order. | AA-39 - Verify that user can access the Checkout Page only after adding the product to the cart. | Test Execution 1 - PASS | None
AA-35 - As a registered client I want to be able to pay for my order. | AA-40 - Verify that only registered users are allowed to access the Checkout Address Page. | Test Execution 1 - PASS | None
AA-35 - As a registered client I want to be able to pay for my order. | AA-41 - Verify that Next Button and Cancel Button are available in the Checkout Address Page. | Test Execution 1 - PASS | None
AA-35 - As a registered client I want to be able to pay for my order. - 1 defect | AA-42 - Verify that Name, Street Address, City, State, Country, Postal code is the mandatory field in the Checkout Address page (Billing Address). | Test Execution 1 - FAIL | AA-46 - In Progress - [Checkout flow section]The mandatory fields from "Billing Andress" section are not marked with"*" symbol.
AA-35 - As a registered client I want to be able to pay for my order. - 1 defect | AA-43 - Verify that error message is displayed when the user enters invalid values in all the fields in the checkout page. | Test Execution 1 - FAIL | AA-45 - In Progress - [Checkout flow section]The order has been submitted after the user completed all the fields from checkout page with invalid values.
AA-34 - "Check out flow" section | None | None | None
AA-33 - [Add to cart section]The user cannot add the same product to the shopping cart after entering a negative value to the "Quantity"input field - 1 defect | AA-38 - Verify that the user can add the same product in the shopping cart,after entering a negative value in the "Quantity"input field | Test Execution 1 - FAIL | AA-33 - Done - [Add to cart section]The user cannot add the same product to the shopping cart after entering a negative value to the "Quantity"input field
AA-23 - Create test conditions for "Add to cart" section | AA-25 - Verify whether shopping cart icon is clickable. | Test Execution 1 - PASS | None
AA-21 - As a registered user I want to be able to add animals to the shopping cart | AA-29 - Verify that the user is redirected to the checkout page after clicking on the “Proceed to checkout “button. | Test Execution 1 - PASS | None
AA-21 - As a registered user I want to be able to add animals to the shopping cart | AA-24 - Check whether the user is able to add the item to the cart. | Test Execution 1 - PASS | None
AA-21 - As a registered user I want to be able to add animals to the shopping cart | AA-26 - Verify that the user is able to change the number of items from the cart. | Test Execution 1 - PASS | None
AA-21 - As a registered user I want to be able to add animals to the shopping cart | AA-27 - Check that subtotal of all items in the cart shows the exact amount. | Test Execution 1 - PASS | None
AA-21 - As a registered user I want to be able to add animals to the shopping cart | AA-28 - Check whether the subtotal is getting changed when the user removes any item from the cart. | Test Execution 1 - PASS | None
AA-21 - As a registered user I want to be able to add animals to the shopping cart - 1 defect | AA-31 - Verify that the user is able to proceed with a negative number like (-1,-2,-3….) | Test Execution 1 - FAIL | AA-37 - Done - [Add to cart section] The input field"Quantity"accept negative value
AA-21 - As a registered user I want to be able to add animals to the shopping cart | AA-32 - Verify if the cart is editable then check that the user is able to enter special characters | Test Execution 1 - PASS | None
AA-21 - As a registered user I want to be able to add animals to the shopping cart | AA-30 - Verify that the products remain in the shopping cart after the user close the browser and reopen the same site. | Test Execution 1 - PASS | None
AA-19 - [Sign Up section] A registered user can create another account using the same email address. - 1 defect | AA-12 - Verify that a registered user cannot create another account using the same email address. | Test Execution 1 - FAIL | AA-19 - Done - [Sign Up section] A registered user can create another account using the same email address.
AA-18 - [Sign Up section] The user can create an account using just letters for password. - 1 defect | AA-13 - Verify that a new user cannot create a password using just letters. | Test Execution 1 - FAIL | AA-18 - Done - [Sign Up section] The user can create an account using just letters for password.
AA-17 - [Sign Up section]The user did not receive a confirmation email after the account was created. - 1 defect | AA-16 - Verify that a confirmation message or email is sent to the user after successful account creation. | Test Execution 1 - FAIL | AA-17 - Done - [Sign Up section]The user did not receive a confirmation email after the account was created.
AA-7 - [Sign Up section] The mandatory fields are not marked with "*" symbol. - 1 defect | AA-6 - Verify that the required/mandatory fields are marked with the ‘*’ symbol | Test Execution 1 - FAIL | AA-7 - Done - [Sign Up section] The mandatory fields are not marked with "*" symbol.
AA-3 - Create test conditions | None | None | None
AA-2 - As a new client I want to be able to create an account | AA-5 - Verify that if all fields are left blank an error message will be displayed. | Test Execution 1 - PASS | None
AA-2 - As a new client I want to be able to create an account - 1 defect | AA-6 - Verify that the required/mandatory fields are marked with the ‘*’ symbol | Test Execution 1 - FAIL | AA-7 - Done - [Sign Up section] The mandatory fields are not marked with "*" symbol.
AA-2 - As a new client I want to be able to create an account | AA-8 - Verify that a validation message is displayed when an incorrect email format is used. | Test Execution 1 - PASS | None
AA-2 - As a new client I want to be able to create an account | AA-9 - Verify that the user cannot create an account by filling out only the email input field | Test Execution 1 - PASS | None
AA-2 - As a new client I want to be able to create an account | AA-10 - Verify that the checkboxes from the profil information section are working. | Test Execution 1 - PASS | None
AA-2 - As a new client I want to be able to create an account | AA-11 - Verify that a new user can choose a language from the dropdown menu | Test Execution 1 - PASS | None
AA-2 - As a new client I want to be able to create an account - 1 defect | AA-12 - Verify that a registered user cannot create another account using the same email address. | Test Execution 1 - FAIL | AA-19 - Done - [Sign Up section] A registered user can create another account using the same email address.
AA-2 - As a new client I want to be able to create an account - 1 defect | AA-13 - Verify that a new user cannot create a password using just letters. | Test Execution 1 - FAIL | AA-18 - Done - [Sign Up section] The user can create an account using just letters for password.
AA-2 - As a new client I want to be able to create an account | AA-15 - Check the Enter button | Test Execution 1 - PASS | None
AA-1 - Sign up section | None | None | None